Wine Tasting Event Planning Check List

Event Name _________________________________________________________

Date and Time _______________________________________________________

5 Weeks Before Event

- Choose theme of event and set sales objectives.

- Contact distributors and gain commitments to participate.

- Contact other partner businesses to participate in the event.

- Order any special promotional signs required from outside companies.

- Assign responsibilities to store employees.

- Flesh out theme, wording for invitations, and overall strategy and tactics.

- Set maximum number of attendees; order glasses, tables, and any other outside resources.

4 Weeks Before Event

- Map out where each partner will set up in the store; confirm of total number of wines to be sampled with tasting notes provided by distributor.

- Make arrangements with partners for exact arrival and setup time and send location map.

- Contact valet parking firm, if required.

3 Weeks Before Event

- Prepare and approve final invitation.

- Segment list and define who will be invited and how they will be contacted (phone, e-mail message, or postal invitation).

- Contact local papers and radio stations with information about the event, if publicity is required.

- Send out invitations with clear RSVP instructions. If RSVP is via telephone, ensure list is available to receptionist to check off acceptance.

- Prepare tasting notes.

2 Weeks Before Event

- Determine “day of” responsibilities (setup time and duties, clean up, etc.).

- Check on responses; send out second wave of mail if needed.

- Reconfirm all partners’ attendance.

## 1 Week Before Event

- Confirm schedule for all employees for the night of event.

- Confirm final number of customers attending (overbook by 20 percent).

## 1 Day Before Event

- Make a final check on all partners and the time they will arrive to set up.

- Make sure all employees and partners park far away from store to maximize space for customers (confirm valet parking if required).

- Confirm “day of” responsibilities.

- Check store to ensure all tables and special equipment is in place.

Wine Tasting Event Planning Check List

## Day of Event

- Make sure all tables are set up after 3 P.M.

- Prepare tables and wine ice buckets where required.

- Greet all partners as they arrive and direct them to set up area.

- Assign staff to set up registration table for arriving customers.

- Have all glassware, tasting sheets, price lists, and promotional signs ready.

- Welcome customers and be available for any problems that arise.

1 Day After Event

- Remove all tables and clean the store.

- Post a thank you to all store employees.

## 1 Week After Event

- Contact all customers who purchased one case or more at event for satisfaction survey.

- Send thank you notes to all suppliers and partners.

- Summarize event evaluations and calculate total plus business that event generated.

- Conduct post-event meeting with store employees for feedback and improvements.